## By Task-Example
UPON REQUEST CONTRACT BUDGET TRACKING LOG
By Task
Tollway Project Manager: |  | PM Name
Consultant: |  | Consultant Company Name | [5 empty] | Total Contract Upper Limit | 3000000
Contract No: |  | XX-XX-XXXX | [5 empty] | Contract DBE commitment | 30%
Date Updated: |  | 2024-05-15 | [5 empty] | Contract VOSB commitment | 5%
Date Today: |  | 2025-04-25
Contract | [9 empty] | Invoices
A | B | C | D | E | F | G | H | I = F X + G X - 1 | J | K | L |  | M | N | O | P = M X + P X - 1
Task No. | Description | Construction Contract No. | Task Notice to Proceed Date | Original Approved Upper Limit $ from NTP | Latest Approved Upper Limit $ | Anticipated Additional Task Need $ | Invoiced to date for this task | Cumulative Approved Task ULC ($) | Task Completion Letter Date | Invoice # | Invoice Period |  | Total Invoice | Invoiced Amt. (DBE) | Invoiced Amt. (VOSB) | Running Total Invoiced to Date
1 | Administration & limted scope activities | N/A | 2022-02-01 | 50000 | 50000 | 0 | 20000 | 50000 | 2022-05-01 | 1 | 2022-01-29 | 2022-02-25 | 5000 | 5000 | 0 | 5000
2 | Task Description | xx-xx-xxxx | 2022-02-03 | 100000 | 100000 | 0 | 90000 | 150000 | 2022-05-02 | 2 | 2022-02-26 | 2022-03-25 | 10000 | 5000 | 1000 | 15000
3 | Task Description | xx-xx-xxxx | 2022-04-22 | 150000 | 150000 | 0 | 120000 | 300000 | 2022-05-03 | 3 | 2022-03-26 | 2022-04-29 | 20000 | 5000 | 1000 | 35000
4 | Task Description | xx-xx-xxxx | 2022-04-06 | 50000 | 50000 | 0 | 20000 | 350000 | 2022-05-04 | 4 | 2022-04-30 | 2022-05-27 | 30000 | 10000 | 1000 | 65000
5 | Task Description | xx-xx-xxxx | 2022-05-09 | 20000 | 20000 | 0 | 10000 | 370000 | 2022-05-05 | 5 | 2022-05-28 | 2022-06-24 | 30000 | 10000 | 1000 | 95000
[10 empty] | 6 | 2022-06-25 | 2022-07-29 | 30000 | 10000 | 5000 | 125000
[10 empty] | 7 | 2022-07-30 | 2022-08-26 | 30000 | 10000 | 5000 | 155000
[10 empty] | 8 | 2022-08-27 | 2022-09-23 | 30000 | 5000 | 5000 | 185000
[10 empty] | 9 | 2022-09-24 | 2022-10-28 | 30000 | 5000 | 5000 | 215000
[10 empty] | 10 | 2022-10-29 | 2022-11-30 | 45000 | 5000 | 5000 | 260000
Contract E: Total; Contract F: 370000; Contract G: 0; Contract H: 260000 |  |  |  | Total Invoiced |  | 260000 | 70000 | 29000
Contract E: Contract Upper Limit; Contract F: 3000000 |  |  |  | Percentage (Invoiced To Date) |  |  | 26.92% | 11.15%
Contract E: Remaining; Contract F: 2630000 |  |  |  | Percentage (Total Contract) |  | 8.667% | 2.333% | 0.9667%
Contract A: Column; Contract B: Instructions; Contract H: Column | Instructions
Contract A: A; Contract B: Assigned Task Number; Contract H: I | Working Task Running Total Estimate, this Column is for the CUR to Estimate the Final Dollar Amount
Contract A: B; Contract B: Task Description; Contract H: J | Task Completion Date - closeout letter date
Contract A: C; Contract B: Construction Contract Number; Contract H: K | The Invoice Number
Contract A: D; Contract B: Notice to Proceed Date for this Task; Contract H: L | Invoice Period
Contract A: E; Contract B: Approved Original Upper Limit Amount As Per The NTP; Contract H: M | Contract Invoice Amount (Not Task Amount)
Contract A: F; Contract B: Approved Original and/or the Approved Revised Upper Limit and or the Approved Final Upper Limit; Contract H: N | Contract Invoice Amount (Not Task Amount) for DBE Only
Contract A: G; Contract B: Anticipated Additional Fee needed to complete task; Contract H: O | Contract Invoice Amount (Not Task Amount) for VOSB Only
Contract A: H; Contract B: Invoiced to date for task; Contract H: P | Invoiced amount Running Total Estimate
If the Task Order is providing Construction Management or design support services, list the corresponding construction contract number.
List Task Order No., Description, and budget from the approved NTPTO process in Trimble Unity Construct (TUC). The Task Order No. and Description will be automatically populated in the 'By Sub' tab.
List Invoice data as submitted via the CINV process in TUC. Include breakdown of invoices submitted by DBE and VOSB firms.
List the Upper Limit and DBE/VOSB commitments from the approved base contract.
Confirm the sum of TOs invoiced to date matches the sum of base contract invoices. Discrepancies will be flagged in red.
Columns E and F should match unless a Supplemental NTPTO has been approved. If a TO has been supplemented, list the new TO amount in column F.
Once a Task Order is complete, list the date of completion letter submitted with the NTPTO-Closeout process in TUC.

## By Sub-Example
UPON REQUEST CONTRACT BUDGET TRACKING LOG | [23 empty] | DBE
By Sub | [23 empty] | VOSB
N/A
Task No. |  | Total | Prime Consultant Name | Sub Name 1 | Sub Name 2 | Sub Name 3 | Sub Name 4 | Sub Name 5 | Sub Name 6 | Sub Name 7 | Sub Name 8 | Sub Name 9 | Sub Name 10 | Sub Name 11 | Sub Name 12 | Sub Name 13 | Sub Name 14 | Sub Name 15 | Sub Name 16 | Sub Name 17 | Sub Name 18 | Sub Name 19 | Sub Name 20
| Description DBE/VOSB Designation |  | N/A | VOSB | VOSB | DBE | N/A | DBE
| Current Consultant Upper Limit | 3000000 | 1750000 | 500000 | 400000 | 150000 | 100000 | 100000
| Contract Percentage | 100% | 58.33% | 16.67% | 13.33% | 5% | 3.333% | 3.333%
| Current Allocated Percentage | 12.33% | 5.667% | 1.25% | 0.9167% | 2.167% | 1.333% | 1%
1 | Administration & limted scope activities | 50000 | 50000
2 | Task Description | 100000 | 50000 |  |  | 50000
3 | Task Description | 150000 | 50000 | 20000 | 20000 | 10000 | 40000 | 10000
4 | Task Description | 50000 | 10000 | 10000 | 7500 | 2500 |  | 20000
5 | Task Description | 20000 | 10000 | 7500 |  | 2500
| Total Allocated | 370000 | 170000 | 37500 | 27500 | 65000 | 40000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Remaining Unallocated | 2630000 | 1580000 | 462500 | 372500 | 85000 | 60000 | 70000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Invoiced to Date | 260000 | 120000 | 40000 | 30000 | 30000 | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GOAL SUMMARY
|  | Category |  | Commitment | Current Allocation
|  | DBE |  | 30% | 3.167%
|  | VOSB |  | 5% | 2.167%
Notes:
Data included in this workbook is for reference only. Please ensure all fields are updated with project-specific data before submittal.
This worksheet is programmed to return error messages and prompts when key information is left blank or budget issues are detected. Please confirm errors have been addressed before submitting to the Tollway. Delete unsused subconsultant columns as necessary.
Blue text cells should be completed by the consultant.
Task Order No. and Description automatically populated from the 'By Task' tab
List Prime consultant, then all subconsultant firms (in alphabetical order). Delete unused columns as necessary.
List the current Upper Limit of each consultant on the contract.
The sum should equal the base contract Upper Limit--discrepancies will be flagged in red.
Enter the total invoiced to date amount for each consultant across all Task Orders.
Enter the Task Order's budget allocated to each consultant assigned to the task.
Enter the consultant's allocated budget for each Task Order they're assigned to.

## By Task
UPON REQUEST CONTRACT BUDGET TRACKING LOG
By Task
Tollway Project Manager: |  | PM Name
Consultant: |  | Consultant Company Name | [5 empty] | Total Contract Upper Limit | 3000000
Contract No: |  | XX-XX-XXXX | [5 empty] | Contract DBE commitment | 30%
Date Updated: |  | 2024-05-15 | [5 empty] | Contract VOSB commitment | 5%
Date Today: |  | 2025-04-25
Contract | [9 empty] | Invoices
A | B | C | D | E | F | G | H | I = F X + G X - 1 | J | K | L |  | M | N | O | P = M X + P X - 1
Task No. | Description | Construction Contract No. | Task Notice to Proceed Date | Original Approved Upper Limit $ from NTP | Latest Approved Upper Limit $ | Anticipated Additional Task Need $ | Invoiced to date for this task | Cumulative Approved Task ULC ($) | Task Completion Letter Date | Invoice # | Invoice Period |  | Total Invoice | Invoiced Amt. (DBE) | Invoiced Amt. (VOSB) | Running Total Invoiced to Date
1 | Administration & limted scope activities | N/A | 2022-02-01 | 50000 | 50000 | 0 | 20000 | 50000 | 2022-05-01 | 1 | 2022-01-29 | 2022-02-25 | 5000 | 5000 | 0 | 5000
2 | Task Description | xx-xx-xxxx | 2022-02-03 | 100000 | 100000 | 0 | 90000 | 150000 | 2022-05-02 | 2 | 2022-02-26 | 2022-03-25 | 10000 | 5000 | 1000 | 15000
3 | Task Description | xx-xx-xxxx | 2022-04-22 | 150000 | 150000 | 0 | 120000 | 300000 | 2022-05-03 | 3 | 2022-03-26 | 2022-04-29 | 20000 | 5000 | 1000 | 35000
4 | Task Description | xx-xx-xxxx | 2022-04-06 | 50000 | 50000 | 0 | 20000 | 350000 | 2022-05-04 | 4 | 2022-04-30 | 2022-05-27 | 30000 | 10000 | 1000 | 65000
5 | Task Description | xx-xx-xxxx | 2022-05-09 | 20000 | 20000 | 0 | 10000 | 370000 | 2022-05-05 | 5 | 2022-05-28 | 2022-06-24 | 30000 | 10000 | 1000 | 95000
[10 empty] | 6 | 2022-06-25 | 2022-07-29 | 30000 | 10000 | 5000 | 125000
[10 empty] | 7 | 2022-07-30 | 2022-08-26 | 30000 | 10000 | 5000 | 155000
[10 empty] | 8 | 2022-08-27 | 2022-09-23 | 30000 | 5000 | 5000 | 185000
[10 empty] | 9 | 2022-09-24 | 2022-10-28 | 30000 | 5000 | 5000 | 215000
[10 empty] | 10 | 2022-10-29 | 2022-11-30 | 45000 | 5000 | 5000 | 260000
Contract E: Total; Contract F: 370000; Contract G: 0; Contract H: 260000 |  |  |  | Total Invoiced |  | 260000 | 70000 | 29000
Contract E: Contract Upper Limit; Contract F: 3000000 |  |  |  | Percentage (Invoiced To Date) |  |  | 26.92% | 11.15%
Contract E: Remaining; Contract F: 2630000 |  |  |  | Percentage (Total Contract) |  | 8.667% | 2.333% | 0.9667%
Contract A: Column; Contract B: Instructions; Contract H: Column | Instructions
Contract A: A; Contract B: Assigned Task Number; Contract H: I | Working Task Running Total Estimate, this Column is for the CUR to Estimate the Final Dollar Amount
Contract A: B; Contract B: Task Description; Contract H: J | Task Completion Date - closeout letter date
Contract A: C; Contract B: Construction Contract Number; Contract H: K | The Invoice Number
Contract A: D; Contract B: Notice to Proceed Date for this Task; Contract H: L | Invoice Period
Contract A: E; Contract B: Approved Original Upper Limit Amount As Per The NTP; Contract H: M | Contract Invoice Amount (Not Task Amount)
Contract A: F; Contract B: Approved Original and/or the Approved Revised Upper Limit and or the Approved Final Upper Limit; Contract H: N | Contract Invoice Amount (Not Task Amount) for DBE Only
Contract A: G; Contract B: Anticipated Additional Fee needed to complete task; Contract H: O | Contract Invoice Amount (Not Task Amount) for VOSB Only
Contract A: H; Contract B: Invoiced to date for task; Contract H: P | Invoiced amount Running Total Estimate
Notes:
Data included in this workbook is for reference only. Please ensure all fields are updated with project-specific data before submittal.
This worksheet is programmed to return error messages and prompts when key information is left blank or budget issues are detected. Please confirm errors have been addressed before submitting to the Tollway.
Blue text cells should be completed by the consultant.

## By Sub
UPON REQUEST CONTRACT BUDGET TRACKING LOG | [23 empty] | DBE
By Sub | [23 empty] | VOSB
N/A
Task No. |  | Total | Prime Consultant Name | Sub Name 1 | Sub Name 2 | Sub Name 3 | Sub Name 4 | Sub Name 5 | Sub Name 6 | Sub Name 7 | Sub Name 8 | Sub Name 9 | Sub Name 10 | Sub Name 11 | Sub Name 12 | Sub Name 13 | Sub Name 14 | Sub Name 15 | Sub Name 16 | Sub Name 17 | Sub Name 18 | Sub Name 19 | Sub Name 20
| Description DBE/VOSB Designation |  | N/A | VOSB | VOSB | DBE | N/A | DBE
| Current Consultant Upper Limit | 3000000 | 1750000 | 500000 | 400000 | 150000 | 100000 | 100000
| Contract Percentage | 100% | 58.33% | 16.67% | 13.33% | 5% | 3.333% | 3.333%
| Current Allocated Percentage | 12.33% | 5.667% | 1.333% | 0.8333% | 2.5% | 1% | 1%
1 | Administration & limted scope activities | 50000 | 50000
2 | Task Description | 100000 | 50000 |  |  | 50000
3 | Task Description | 150000 | 50000 | 20000 | 20000 | 20000 | 30000 | 10000
4 | Task Description | 50000 | 10000 | 10000 | 5000 | 5000 |  | 20000
5 | Task Description | 20000 | 10000 | 10000
| Total Allocated | 370000 | 170000 | 40000 | 25000 | 75000 | 30000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Remaining Unallocated | 2630000 | 1580000 | 460000 | 375000 | 75000 | 70000 | 70000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Invoiced to Date | 260000 | 120000 | 40000 | 30000 | 30000 | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GOAL SUMMARY
|  | Category |  | Commitment | Current Allocation
|  | DBE |  | 30% | 3.5%
|  | VOSB |  | 5% | 2.167%
Notes:
Data included in this workbook is for reference only. Please ensure all fields are updated with project-specific data before submittal.
This worksheet is programmed to return error messages and prompts when key information is left blank or budget issues are detected. Please confirm errors have been addressed before submitting to the Tollway. Delete unsused subconsultant columns as necessary.
Blue text cells should be completed by the consultant.