## Summary
THE ILLINOIS STATE TOLL HIGHWAY AUTHORITY
ACCELERATED BRIDGE CONSTRUCTION (ABC) - BRIDGE LIFE CYCLE COMPARISON (BLCC) TOOL
Prepared By | XX |  | Prepared On | xx/xx/xxxx
Checked By | XX |  | Checked On | xx/xx/xxxx
Bridge No. | XXXXX |  | Mile Post | xx.xx
Location | xxxxxx
ABC BLCC Tool | [7 empty] | December 2016
Note to User: Refer to Structure Design Manual Article 27.3.2 for general guidance on using this tool.
TOTAL ABC BLCC RATING SCORE SUMMARY
Total ABC BLCC Rating Score = 0.33(IC)+ 0.34(TIC)+ 0.33(MC)
DIRECTIONS FOR USER: | [8 empty] | Conventional | CIP | Coventional | Alt # 1
[9 empty] | ABC | Precast | Lateral Slide | Alt # 2
|  | User to Input values | [6 empty] | N/A | Steel | SPMT | Alt # 3
[10 empty] | N/A | Longitudinal Launch | Alt # 4
| User may elect to add additional bridge alternatives to the ABC BLCC Tool to accurately compare all options. | [9 empty] | Crane Based | Alt # 5
[9 empty] | CIP | CIP | N/A | N/A
| Construction Type = Enter the type of construction (Conventional or ABC) | [7 empty] | Precast Panels | PBES
| Deck = Enter the type of deck material (CIP or Precast Panels) | [7 empty] | N/A | N/A
Super = Enter the type of Superstructure (CIP, Precast or Steel)
Sub = Enter the type of substructure (CIP or PBES)
Method = Enter the type of construction method (Conventional, Lateral Slide, SPMT, Longitudinal Launch, Crane Based)
Bridge Alternates Investigated
| Name |  | Construction Type | Deck | Super | Sub | Method
Bridge Alternative #1
Bridge Alternative #2
Bridge Alternative #3
Bridge Alternative #4
Bridge Alternative #5
Manually Input results for different Bridge Alternatives Investigated:
Total ABC BLCC Rating Score
|  |  | Alt #1 | Alt #2 | Alt #3 | Alt #4 | Alt #5
Initial Costs (IC)
Traffic Impact Costs (TIC)
Maintenance Costs (MC)
| Total ABC BLCC Rating Score |  | 0 | 0 | 0 | 0 | 0
User may elect to add additional Recommended Bridge Alternatives to the ABC BLCC Tool to evaluate further in the Bridge Type Study and perform a cost comparison.
Recommended Bridge Alternatives
Bridge Alternatives to Consider Based on Total ABC BLCC Rating Score:

## BLCC
THE ILLINOIS STATE TOLL HIGHWAY AUTHORITY
ACCELERATED BRIDGE CONSTRUCTION (ABC) - BRIDGE LIFE CYCLE COMPARISON (BLCC) TOOL
Prepared By | XX | Prepared On | xx/xx/xxxx
Checked By | XX | Checked On | xx/xx/xxxx
Bridge No. | XXXXX | Mile Post | xx.xx
Location | xxxxxx
ABC BLCC Tool | [6 empty] | December 2016
Note to User: Refer to Structure Design Manual Article 27.3.2 for general guidance on using this tool.
INDIVIDUAL ABC BLCC RATING SCORE INPUT
INITIAL COSTS (IC)
Total Labor |  | 1 | Estimated construction time >= 18 months
(On-Site and Off-Site) |  | 2 | 13 months <= Estimated construction time < 18 months
|  | 3 | 8 months <= Estimated construction time < 13 months |  |  |  |  | 1
|  | 4 | 3 months <= Estimated construction time < 8 months |  |  |  |  | 2
|  | 5 | Estimated construction time < 3 months |  |  |  |  | 3
4
Deck Material |  | 1 | Deck type is cast-in-place concrete |  |  |  |  | 5
|  | 2 | Deck type is precast concrete panels
Superstructure Material |  | 1 | Superstructure type is cast-in-place concrete
|  | 2 | Superstructure type is precast concrete or steel
Substructure Material |  | 1 | Substructure type is cast-in-place concrete
|  | 2 | Substructure type is precast concrete
Equipment |  | 1 | Self-Propelled Modular Transport equipment required
|  | 2 | Bridge Slide-In equipment required
|  | 3 | Specialty Crane Based equipment required
|  | 4 | Prefabricated Bridge Element System or Longitudinal Launch required
|  | 5 | Typical cast-in-place concrete/steel construction equipment required
Agency Costs |  | 1 | Extensive agency coordination
|  | 2 | Moderate agency coordination
|  | 3 | Normal agency coordination
Right-of-Way |  | 1 | Required R.O.W. acquisition > 1 acre
|  | 2 | 0.5 acres < Required R.O.W. acquisition <= 1 acre
|  | 3 | 0.25 acres < Required R.O.W. acquisition <= 0.5 acres
|  | 4 | 0 acres < Required R.O.W. acquisition <= 0.25 acres
|  | 5 | Required R.O.W. acquisition = 0 acres
Environmental Impact Costs |  | 1 | Maximum impact
|  | 2 | Medium impact
|  | 3 | Minimum impact
|  | 4 | No Impact
TRAFFIC IMPACT COSTS (TIC)
Maintenance of Traffic Costs |  | 1 | Extended duration with multiple staging
|  | 2 | Extended duration with simple MOT
|  | 3 | Normal duration
|  | 4 | Short duration with multiple staging
|  | 5 | Short duration with simple MOT
Economic Impacts |  | 1 | High business impact
|  | 2 | Medium business impact
|  | 3 | Low business impact
Railroad/ Waterway Impacts |  | 1 | Complete closure
|  | 2 | Extended duration, disruption or closure
|  | 3 | Normal duration, disruption or closure
|  | 4 | Short duration, disruption or closure
|  | 5 | No disruption or closure of Railroads/Waterways
Note:
Service disruptions (including traveler delay and revenue impacts) are not directly included in the ABC BLCC Tool. Additional analysis required if requested by the Illinois Tollway.
MAINTENANCE COSTS (MC)
Maintenance / Rehabilitation |  | 1 | If No Precast element types are used (Highest Repair Frequency)
Life Cycle Costs |  | 2 | If One Precast element type is used
(Frequency) |  | 3 | If Two Precast element types are used
|  | 4 | If Three or more Precast element types are used (Lowest Repair Frequency)
Cost of Repair |  | 1 | If Three of the Listed Materials are used (Most Expensive Cost)
(Material, Labor and Time) |  | 2 | If Two of the Listed Materials are used
|  | 3 | If One of the Listed Materials are used
|  | 4 | If None of the Listed Materials are used (Cheapest Cost)
Note:
Listed Material: Precast Deck Panels, Steel Girders, PBES Substructure.
Total Replacement Costs |  | 1 | If only super is precast or if only sub is precast or neither
(Estimated Service Life) |  | 2 | Precast Beams and Precast Substructure
Note:
The decision to replace structure is based on superstructure and substructure condition. Excludes deck.
Future TIC for Routine |  | 1 | Weekday Peak shift or Extended MOT Duration or Major Impact
Maintenance |  | 2 | Weekend or night time closure or Medium MOT Duration or Medium Impact
|  | 3 | Off peak closure or Shorter MOT Duration or Minimal Impact
|  | 4 | No Closure or Shortest MOT Duration or No Impact
Future TIC for Rehabilitation |  | 1 | Weekday Peak shift or Extended MOT Duration or Major Impact
and Replacement |  | 2 | Weekend or night time closure or Medium MOT Duration or Medium Impact
|  | 3 | Off peak closure or Shorter MOT Duration or Minimal Impact
|  | 4 | No Closure or Shortest MOT Duration or No Impact
Joint Durability |  | 1 | Additional joints between precast elements
|  | 2 | Typical Jointed Bridge
|  | 3 | Jointless Bridge
Unforseen Performance |  | 1 | High (More than one PBES element)
(Risk) |  | 2 | Medium (Single PBES element )
|  | 3 | None or Low (Conventional Construction material)
Salvage Value |  | 1 | Precast Concrete Beam
|  | 2 | Steel Girders
Note: Do not adjust weight factors without prior approval from the Illinois Tollway.
Individual ABC BLCC Rating Score = (Total Score)/(Max. Score)*100
Total ABC BLCC Rating Score = 0.33(IC) + 0.34(TIC) + 0.33(MC)
INITIAL COSTS (IC)
| Variable |  | Weight | Adjusted | Maximum | Max Adjusted
|  | Score | Factor | Score | Score | Score
| Total Labor | 0 | 10 | 0 | 5 | 50
| Deck Material | 0 | 10 | 0 | 2 | 20
| Superstructure Material | 0 | 10 | 0 | 2 | 20
| Substructure Material | 0 | 10 | 0 | 2 | 20
| Equipment | 0 | 10 | 0 | 5 | 50
| Agency Costs | 0 | 5 | 0 | 3 | 15
| Right-of-Way | 0 | 5 | 0 | 5 | 25
| Environmental Impact Costs | 0 | 3 | 0 | 4 | 12
|  |  | Total Score | 0 |  | 212
|  | IC ABC BLCC Rating Score: |  | 0 |  | (33% of Total Score)
TRAFFIC IMPACT COSTS (TIC)
| Variable |  | Weight | Adjusted | Maximum | Max Adjusted
|  | Score | Factor | Score | Score | Score
| Maintenance of Traffic Costs | 0 | 10 | 0 | 5 | 50
| Economic Impacts | 0 | 5 | 0 | 3 | 15
| Railroad/Waterway Impacts | 0 | 5 | 0 | 5 | 25
|  |  | Total Score | 0 |  | 90
|  | TIC ABC BLCC Rating Score: |  | 0 |  | (34% of Total Score)
MAINTENANCE COSTS (MC)
| Variable |  | Weight | Adjusted | Maximum | Max Adjusted
|  | Score | Factor | Score | Score | Score
| Maintenance / Rehabilitation Life Cycle Costs | 0 | 10 | 0 | 4 | 40
| Cost of Repair | 0 | 10 | 0 | 4 | 40
| Total Replacement Costs | 0 | 10 | 0 | 2 | 20
| Future TIC for Routine Maintenance | 0 | 5 | 0 | 4 | 20
| Future TIC for Rehabilitation and Replacement | 0 | 3 | 0 | 4 | 12
| Joint Durability | 0 | 5 | 0 | 3 | 15
| Unforseen Performance | 0 | 3 | 0 | 3 | 9
| Salvage Value | 0 | 3 | 0 | 2 | 6
|  |  | Total Score | 0 |  | 162
|  | MC ABC BLCC Rating Score: |  | 0 |  | (33% of Total Score)
[5 empty] | TOTAL ABC BLCC Rating Score: | 0

## BLCC Guidance
THE ILLINOIS STATE TOLL HIGHWAY AUTHORITY
ACCELERATED BRIDGE CONSTRUCTION (ABC) - BRIDGE LIFE CYCLE COMPARISON (BLCC) TOOL
CONSTRAINT DESCRIPTION TABLE
INITIAL COSTS (IC)
Constraint | Description
Total Labor | This accounts for both on-site and off-site labor costs during the duration of the construction project. This constraint shall include time for items specifically on the bridge construction site and time for items constructed "near-site" (such as items constructed at a site adjacent to the bridge and moved into place via slide-ins or SPMT's). Projects that require longer construction periods will generally lead to higher labor costs and will have lower scores in this category.
Deck Material | This accounts for the material cost of the deck portion of the construction project. Cast-in-place concrete decks are assumed to have a higher initial cost due to the need to construct and strip forms and place concrete on-site and will have lower scores in this category. If cost breakdowns for a given project suggest otherwise, the BLCC scores can be adjusted accordingly.
Superstructure Material | This accounts for the material cost of the superstructure portion of the construction project. A precast concrete or steel superstructure is assumed to have the the cheapest initial cost and will have higher scores in this category. If cost breakdowns for a given project suggest otherwise, the BLCC scores can be adjusted accordingly.
Substructure Material | This accounts for the material cost of the substructure portion of the construction project. Precast concrete substructures are assumed to have the cheapest initial cost and will have higher scores in this category. If cost breakdowns for a given project suggest otherwise, the BLCC scores can be adjusted accordingly.
Equipment | This accounts for the equipment cost of the construction project. Conventional equipment that is used for normal concrete and/or steel construction will be considered the most benefitial. As the equipment required becomes more complex and expensive, the scores in this category will decrease. The need for specialized equipment, such as that required for Heavy Lifting or Gantry Cranes, Self-Propelled Modular Transports and Slide-Ins, shall result in lower scores in this category.
Agency Costs | This accounts for the additional costs incurred by the Illinois Tollway as an agency during the construction project. "Normal agency coordination" shall defined for conventional construction methods which present the least likelihood for agency costs during construction and will receive the highest scores in this category. Construction projects that use methods that are less familiar to the agency and contracting community present a higher likelihood for more agency involvement and coordination and will receive lower scores in this category.
Right-of-Way | This accounts for the Right-of-Way aquisition costs required for the bridge construction only. Smaller areas of required Right-of-Way acquisition shall receive higher scores in this category. Scores shall be increased at the descretion of the User if large areas of temporary easement are required. ROW acquisition required for roadway construction (alignment shift, widening etc) should not be included in this variable.
Environmental Impact Costs | This accounts for the cost to mitigate environmental impacts during construction activities and for items requiring permiting that could delay the construction schedule. The environmental impacts can include impacts to streams and lakes, presence of endangered or protected species and potential for contaminated soils. Projects can also be impacted by noise, wetlands, air quality, natural resources, land use or extreme weather which could incurr cost or limit the allowable construction windows. The maximum impact of a particular type shall govern the overall score.
TRAFFIC IMPACT COSTS (TIC)
Constraint | Description
Maintenance of Traffic Costs | This accounts for the safety of workers and travelers, and the amount of time and cost of staging during the construction process. "Short duration" shall be defined as a duration of 3 months or less, "normal duration" shall be defined as a duration between 3 and 9 months, and "extended duration" shall be defined as a duration of 9 months or greater. "Simple MOT scheme" shall be defined as construction with 2 stages or less. "Multiple Staging" shall be defined as construction with more than 2 stages. More complex, higher duration MOT will cost more and shall receive lower scores.
Economic Impacts | This accounts for the negative economic impacts on local businesses and limited access for customer and employee traffic at a given site caused by construction activities. A bridge alternative affecting larger population with more business impacts will receive a lower score.
Railroad/Waterway Impacts | This accounts for the impact to railroad or waterway traffic and users due to construction activities. Bridge alternatives requiring longer track closures or work in waterways, particularly navigable waterways, shall receive a low score. "Short duration" shall be defined as a duration of 1 week or less, "normal duration" shall be defined as a duration between 1 week and 3 months, and "extended duration" shall be defined as a duration of 3 months or greater.
MAINTENANCE COSTS (MC)
Constraint | Description
Maintenance / Rehabilitation Life Cycle Costs | This accounts for the cost of routine maintenance, repair and rehabilitation to the structure. It is assumed that precast elements have a longer life cycle than CIP elements and would require less frequent repairs than CIP elements. The more precast element types utilized, the longer the service life and less frequent repair cycle. Refer to Structure Design Manual article 27.4.1 for precast element types to consider. Precast concrete beams should not be considered as a precast element for this variable. If multiple of the same type of precast elements are utilized such as precast pier columns, the scoring shall be based on one precast element type used. Scores shall be increased at the descretion of the User if precast deck panels are used since the deck condition typically controls the frequency of repair.
Cost of Repair | This accounts for the cost to repair different components of the bridge. The cost should be based on the quantity, material, labor and time to perform the repair and not the frequency or cycle of repair. It is assumed that precast deck panels will cost more to repair than CIP decks, since the entire panel will most likely be replaced, requiring fabrication, shipping, etc. It is assumed that steel girders will cost more to repair than precast beams since steel girders require more repair over time. It is assumed that precast substructure elements will cost more to repair than CIP substructure since PBES may require additional joints and grout ports. Therefore, if the bridge alternative under consideration utilizes any of these items, it would cost more to repair than if not utilizing.
Total Replacement Costs | This accounts for the cost for total replacement of the structure. New Illinois Tollway structures have a 100 year service life and the decision to replace the structure is based on the condition/age of the girder/beams and substructure. The deck condition/age does not factor into the decision to completely replace the structure. The structure can be easily re-decked. The scoring criteria is based on PBES elements having a longer life cycle than CIP elements. However, the service life will be determined by the worst condition of either the girders/beams or substructure. The assumption is that utilizing both precast beams and precast substructure will extend the service life of the bridge. If only one precast element is used, the corresponding non-precast element will control the service life of the structure.
Future TIC for Routine Maintenance | This accounts for the cost associated with future routine maintenance of the structure. This item covers all the constraints listed in theTraffic Impact Costs (TIC). The worst condition of the TIC variables (MOT duration or complexity of staging, economical, railroad, waterway, or vulnerability impacts) impacted during future routine mainentance shall govern the scoring.
Future TIC for Rehabilitation and Replacement | This accounts for the cost associated with future rehabilitation or replacement of the structure. This item covers all the constraints listed in theTraffic Impact Costs (TIC). The worst condition of the TIC variables (MOT duration or complexity of staging, economical, railroad, waterway, or vulnerability impacts) impacted during future rehabilitation or replacement shall govern the scoring.
Joint Durability | This accounts for the maintenance cost required to repair joints on the structure. PBES elements tend to require additional joints which may create durability issues. Durability issues could lead to lower service life for the structure.
Unforseen Performance | This accounts for cost associated with maintenance for unforseen performance of PBES elements. PBES elements could offer a greater risk for maintenance compared to CIP or conventional components since historical data or performance data is not readily available for these elements. In addition, the PBES elements have not been widely used on the Illinois Tollway; therefore, Contractors have limited experience with this type of construction. Precast concrete beams shall not be considered a PBES for this scoring.
Salvage Value | This accounts for the salvage value of the superstructure. Steel girders are more easily recycled than Precast Concrete Beams.